## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Individual task: Python, Sql, Model Research | MUST HAVE | No Dependency | Arthi Bandari | 3- Completed
S1 | S1 | US-001 | Introduction to AI-Driven Code Reviewer Project | MUST HAVE | No Dependency | Arthi Bandari | 3- Completed
S1 | S1 | US-001 | Understanding Project Workflow, Architecture Diagram and Goal Documentation | MUST HAVE | AWS Architecture Diagram | Arthi Bandari | 3- Completed
S2 | S2 | US-001 | Agile Documentation Discussion | MUST HAVE | No Dependency | Arthi Bandari | 3- Completed
S2 | S2 | US-001 | Learn and research frontend development basics | MUST HAVE | Research from AI Tools | Arthi Bandari | 3- Completed
S2 | S2 | US-001 | Learn and Research backend development basics | MUST HAVE | Research from AI Tools | Arthi Bandari | 3- Completed
S3 | S3 | US-001 | Design different pages for the project frontend | MUST HAVE | VS code & Github | Arthi Bandari | 3- Completed
S4 | S4 | US-001 | Start backend development setup | MUST HAVE | VS code & Github | Arthi Bandari | 3- Completed
S5 | S5 | US-001 | Integrate GPT API for code review feedback | MUST HAVE | Static Code Analysis | Arthi Bandari | 3- Completed
S6 | S6 | US-001 | Integrate frontend with backend APIs | MUST HAVE | UI Design and API Integration | Arthi Bandari | 3- Completed
S7 | S7 | US-001 | Perform testing on backend modules | MUST HAVE | Backend Modules | Arthi Bandari | 3- Completed
S8 | S8 | US-001 | Deploying the project | MUST HAVE | Streamlit on EC2 | Arthi Bandari | 3- Completed
S9 | S9 | US-001 | PPT Presentation practice and Project Demo Practice | MUST HAVE | PPT & Project | Arthi Bandari | 3- Completed
S10 | S10 | US-001 | PPT Presentation practice and Project Demo shown to internal Team | MUST HAVE | PPT & Project | Arthi Bandari | 2- In Progress
S11 | S11 | US-001 | PPT Presentation practice and Project Demo shown to Infosys Team | MUST HAVE | PPT & Project | Arthi Bandari | 2- In Progress
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 106 | 30 | 17 | 18 | 14 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Individual task: Python, Sql, Model Research | 2025-12-27 | 2026-01-08 | Arthi Bandari | Coding | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Introduction to AI-Driven Code Reviewer Project | 2026-01-09 | 2026-01-12 | Arthi Bandari | Others | 3- Completed | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 3 | Understanding Project Workflow, Architecture Diagram and Goal Documentation | 2026-01-05 | 2026-01-07 | Arthi Bandari | Others | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 4 | Agile Documentation Discussion (Agile Template, Defect Tracker, Unit Testing) | 2026-01-05 | 2026-01-09 | Arthi Bandari | Others | 3- Completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 5 | Learn and research frontend development backend and AI basics | 2026-01-10 | 2026-01-23 | Arthi Bandari | Others | 3- Completed | 12 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 6 | Frontend Development | 2026-01-23 | 2026-02-01 | Arthi Bandari | Coding | 3- Completed | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 7 | Backend Development | 2026-01-24 | 2026-02-11 | Arthi Bandari | Coding | 3- Completed | 10 | 3 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 8 | Integrating Backend into Frontend | 2026-02-12 | 2026-02-17 | Arthi Bandari | Coding | 3- Completed | 7 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 8 | Project Discussion Module 1 ( Testing, Improvements) | 2026-02-19 | 2026-02-21 | Arthi Bandari | System Test | 3- Completed | 12 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 9 | Project Discussion Module 2 (Testing, Improvements) | 2026-02-22 | 2026-02-21 | Arthi Bandari | Integration Test | 3- Completed | 12 | 4 | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 10 | PPT Presentaion practice and Project Demo | 2026-02-24 | 2026-02-24 | Arthi Bandari | Others | 3- Completed | 10 | 3 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 11 | PPT Presentation practice and Project Demo shown to internal Team | 2026-02-26 | 2026-02-27 | Arthi Bandari | Others | 2- In Progress | 12 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 12 | PPT Presentation practice and Project Demo Practice to Infosys Team | 2026-02-28 |  | Arthi Bandari | Others | 2- In Progress | 10 | Day 1: 3; Day 2: 0; Day 3: 2; Day 4: 2; Day 5: 1; Day 6: 1; Day 7: 1; Day 8: 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Lack of clarity on project requirements for the AI Code Reviewer | Conducted requirement discussion meeting with team and mentors
Sprint 1 | Day 4 | Confusion in defining architecture for backend + GPT integration | Conducted brainstorming session and finalized initial architecture diagram
Sprint 2 | Day 6 | Difficulty finalizing UI flow for Developer, Agent, Status, Testing pages | Reviewed wireframes and finalized screen structure with the team.
Sprint 2 | Day 7 | Ambiguity in component placement for dashboard and code viewer | Conducted a frontend design review meeting and locked UI components
Sprint 2 | Day 9 | Unsure about frontend–backend communication endpoints | Coordinated with backend team and documented required API
Sprint 3 | Day 12 | Issues in setting up backend project structure | Team members worked together and did project folder and structure finalized
Sprint 3 | Day 13 | Error integrating static code analysis tools | Tested configurations and fixed installation issues with team support
Sprint 4 | Day 16 | Output variations during scoring and severity calculations | Standardized scoring logic and tested with sample code files
Sprint 5 | Day 23 | Performance issues during multiple code uploads | Performed optimization and added retry handling

## Retrospection
| Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-01-30 | 2026-01-06 | Arthi Bandari | Reviewing project requirements and architecture docmentation | Stop assuming architecture flow without validation | Participating in discussions and meetings | Conducted requirement clarification meeting and finalized basic architecture
2 | Sprint 2 | 2026-01-17 | 2026-01-30 | Arthi Bandari | Start creating UI component mapping for dashboard + code viewer | Stop delaying frontend structure decisions | Continue maintaining Agile task updates | Completed UI wireframes, dashboard flow, and confirmed frontend component layout
3 | Sprint 3 | 2026-01-31 | 2026-02-13 | Arthi Bandari | Start building backend API layer and code analysis logic step-by-step | Stop working without testing intermediate outputs | Continue debugging collaboratively with tea | Developed backend structure (Flask/FastAPI), integrated static analysis tools, resolved API issues
4 | sprint 4 | 2026-02-15 | 2026-02-22 | Arthi Bandari | Reviewing project requirements and architecture docmentation | Stop overloading UI screens with too many features in one sprint | Continue refining and reviewing modules | Completed scoring standardization, improved performance, finalized demo and presentation materials